### Part B

DRAFT CONTRACT AND SPECIAL CONDITIONS, INCLUDING ANNEXES

# DRAFT CONTRACT

SUPPLY CONTRACT FOR EUROPEAN

UNION EXTERNAL ACTIONS

No IPA3.3.2.2.01.04.c04.

financed from the EU General Budget

Hrvatske Vode (Croatian Waters)

Ulica Grada Vukovara 220

HR – 10000 Zagreb

("the Contracting Authority")

of the one part,

and

<Full official name of Contractor>

[Legal status/title]

[Official registration number]

[Full official address]

[VAT number]

(“the Contractor”)

of the other part,

have agreed as follows:

- The Supply of Equipment for Water Supply and Sewerage System with Wastewater Treatment Plant for Slavonski Brod

- Identification number: EuropeAid/130057/D/SUP/HR

- Article 1	Subject

  - The subject of the contract shall be the supply, delivery, training and after-sales services for Lot 1 and Lot 2 of the following supplies:

| Lot no 1 - Sewerage Suction/Flushing Vehicles |  |  |
| --- | --- | --- |
| Item | Description | Quantity |
| 1 | Combination Suction /Flushing Vehicle 12,5 m3 | 1 |
| 2 | Suction Vehicle 8 m3 | 1 |

| Lot no 2 - CCTV sewer inspection camera equipment installed in a customized van |  |  |
| --- | --- | --- |
| Item | Description | Quantity |
| 1 | CCTV sewer inspection camera equipment installed in a customized van | 1 |

Training for Lot 1

| Training | Operational training for 10 days in Slavonski Brod for at least two (2) persons per each vehicle (Items 1 and 2). The training should be provided in Croatian language. |
| --- | --- |

Training for Lot 2

| Training | Operational training for 5 days for at least 2 persons. The training should be provided in Croatian language. |
| --- | --- |

After-sales services for Lot 1 and Lot 2

| Response time | 4 h response time on-site next business day (9-17 h) during 3 years of warranty (1 year standard waranty and 2 years commercial warranty) |
| --- | --- |
| Repair time | Maximum 1 month time period in case that major defaults are detected and maximum 10 days period in case of minor repairs during 3 years of warranty (1 year standard warranty and 2 years commercial warranty) |
| Commercial warranty covering all the supplied equipment and its components | 2 years, beginning from the expiry of the one year standard warranty |

The place of acceptance of the supplies shall be at the address of Vodovod d.o.o. Slavonski Brod, Nikole Zrinskog 25, HR-35000 Slavonski Brod, and the Incoterm applicable shall be DDU. The implementation period of tasks for Lot 1 shall last 275 days for Lot 1 and 231 days for Lot 2, starting from day of issuance of Commencement Order and ending on the day of issuance of the certificate of Provisional Acceptance. The implementation period will include delivery period of 210 days for Lot 1 and 180 days for Lot 2.

  - The Contractor shall comply strictly with the terms of the Special Conditions and the technical annex.

- Article 2 	Origin

2.1	The supplies must originate in a Member State of the European Union or a country covered and/or authorised by the specific instrument applicable to the IPA programme.

2.2	A certificate of origin for the supplies must be provided by the Contractor at the latest when it requests provisional acceptance of the supplies. Failure to comply with this condition may result in the termination of the contract.

2.3	The origin of the goods shall be determined according to the Community Customs Code or the international agreements to which the country is a signatory.

- Article 3	Price

3.1	The price of the supplies shall be that shown on the financial offer (specimen in Annex IV). The total maximum contract price shall be: __________ EUR (<amount in words>), excluding VAT and other taxes of which

51,75% (<amount in figures>EUR) is paid by IPA and

48,25% (<amount in figures>EUR) is paid by the national co-financing.

In accordance with Article 13 of Annex A to the Framework Agreement between the European Commission and the Government of the Republic of Croatia concerning the European Community aid programmes (Official Gazettes of the Republic of Croatia 8/2002 and 11/2002) and line e), paragraph (1) of Article 25 and lines b) and d), paragraph (2) of Article 26 of the Framework Agreement between the Government of the Republic of Croatia and the Commission of the European Communities concerning the principles of co-operation in the field of the financial aid provided to the Republic of Croatia by the European Community for the implementation of assistance within the framework of the Instrument of Pre-Accession Assistance (IPA) (Official Gazette of the Republic of Croatia 10/2007), the Contract is exempted from VAT, customs duties, import duties and other fiscal charges.

3.2 	Payments shall be made in accordance with the General and/or Special Conditions (Articles 26 to 28).

- Article 4	Order of precedence of contract documents

The contract is made up of the following documents, in order of precedence:

- the contract agreement;

- the Special Conditions

- the General Conditions (Annex I);

- the Technical Specifications (Annex II) [including clarifications before the deadline for submission of tenders];

- the Technical Offer (Annex III) [including clarifications from the tenderer provided during tender evaluation];

- the budget breakdown (Annex IV);

- specified forms and other relevant documents (Annex V).

- The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above.

Done in English in three originals, one original being for the Contracting Authority, one original being for the European Commission, and one original being for the Contractor.

| For the Contractor |  |  | For the Contracting Authority |  |  |
| --- | --- | --- | --- | --- | --- |
| Name: |  |  | Name: | Mr. Siniša Širac PhD |  |
| Title: |  |  | Title: | Deputy General Manager/Head of Implementing Body |  |
| Signature: |  |  | Signature: |  |  |
| Date: |  |  | Date: |  |  |
| Endorsed for financing by the European Union |  |  |  |  |  |
| Name: | Mr. Paul Vandoren |  |  |  |  |
| Title: | Head of the EU Delegation to the Republic of Croatia |  |  |  |  |
| Signature: |  |  |  |  |  |
| Date: |  |  |  |  |  |

Where the contracting party is an individual.

Where applicable. For individuals, mention their ID card or passport or equivalent document - number

Except where the contracting party is not VAT registered.

DDU (Delivered Duty Unpaid) - Incoterms 2000 International Chamber of Commerce - http://www.iccwbo.org/incoterms/id3040/index.html